## Overview
Project | QA Test Plan - Top 1% Manual Portfolio
Generated On | 2025-12-09
Prepared By | Arti Yadav (Portfolio)
Version | 1.0
Objectives
- Provide comprehensive test coverage for Login, Signup, CRM Contacts, SQL and API modules.
- Define test strategy, environments, entry/exit criteria, schedule, risks, and deliverables.
Assumptions
- Test environment will be provisioned as defined in Test Environment sheet.
- API documentation and DB access will be available for integration tests.

## Scope
Scope Items
Functional testing of Login, Signup (Email/Phone+OTP+Password), CRM Contacts, API endpoints, SQL validations
Negative, boundary, security, and UX test cases for the modules listed
Import/export, pagination, search/filter and permission checks in CRM Contacts
API contract validation, error codes, pagination, rate-limit and auth flows
Out of Scope
Automated test execution (only manual test design included)
Performance/load testing beyond smoke-level response time checks
Third-party integrations not yet documented

## Test Strategy
Test Level | Approach / Tools | Notes
Unit | N/A (handled by devs) | Focus on integration & system
Integration | Manual API validation, DB checks | Use Postman or API client for manual verification
System | End-to-end manual test scenarios | Covers user journeys across modules
Regression | Maintain manual regression suite in Excel | Run before major releases
Security | Manual security checks + checklist | SQL injection, XSS, auth bypasses
UX/Accessibility | Manual heuristics and basic WCAG checks | Labels, tabindex, error messaging

## Test Environment
Environment Name | Details
Dev | Latest build; not stable; used by developers
QA | Stable build for testing; DB with test data; API endpoints staging
Prod-Replica | Read-only replica for performance smoke checks
Environment Configuration
- Web: Chrome (latest), Firefox (latest) on Windows, macOS, Android (mobile)
- API: Staging base URL, Auth token creds provided to QA
- DB: Test schema with sample data; read/write access for QA as required

## EntryExitCriteria
Entry Criteria
Build deployed to QA environment
Smoke tests pass (basic login and critical flows)
Test data available and DB accessible
Test team resourced and test artifacts available (RTM, test cases)
Exit Criteria
All critical and high priority test cases passed or have accepted defects
No open Severity-1 defects blocking release
Test coverage per RTM marked as Covered for release features
Test summary report prepared and signed off

## Schedule
Phase | Start Date | End Date | Duration (days) | Owner
Test Planning | 2025-12-09 | 2025-12-12 | 3 | QA Lead
Test Case Design | 2025-12-13 | 2025-12-19 | 7 | QA Engineers
Environment Setup | 2025-12-09 | 2025-12-11 | 2 | DevOps
Test Execution (Functional) | 2025-12-20 | 2025-12-29 | 10 | QA Team
Defect Triage & Retest | 2025-12-30 | 2026-01-03 | 5 | QA/Dev
Test Closure | 2026-01-04 | 2026-01-06 | 3 | QA Lead

## Roles_R&R
Role | Name / Example | Responsibility
QA Lead | Arti (Portfolio) | Plan & coordinate testing activities, RTM sign-off
QA Engineer | QA Team | Design & execute test cases, report defects
Developer | Dev Team | Fix defects, provide builds and DB support
DevOps | Infrastructure | Provision environments & monitor builds
Product Owner | PO | Clarify requirements, prioritize defects

## Risks_Mitigation
Risk | Impact | Probability | Mitigation
Environment instability | High | Medium | Use stable QA environment; snapshot DBs
Incomplete requirements | High | Medium | Lock requirements and use RTM to track changes
Delayed builds | Medium | High | Parallel testing on stable builds & smoke checks
Data privacy concerns | High | Low | Use anonymized test data and prod replica policies

## Deliverables
Deliverable | Owner | Format/Location
RTM | QA Lead | TestCases/RTM/RTM_Advanced.xlsx
Test Cases (Excel) | QA Engineers | TestCases/*/*.xlsx
Test Plan | QA Lead | TestCases/TestPlan/TestPlan_Advanced.xlsx
Test Summary Report | QA Lead | Reports/TestSummary_<date>.xlsx
Defect Log | QA Team | BugTracker/ (Jira/GitHub Issues)

## Coverage_Matrix
Module | Requirement ID | Mapped Test Cases | Mapped Files | Coverage Status
Login | REQ-LOGIN-001 | LGN_001, LGN_002 | TestCases/LoginModule/Login_All.xlsx | Covered
Signup | REQ-SIGN-001 | SGN_001, SGN_002 | TestCases/SignupModule/Signup_Advanced.xlsx | Not Tested
CRM Contacts | REQ-CRM-001 | CRM_CNT_001..005 | TestCases/CRMContactsModule/CRM_Contacts_Advanced.xlsx | Covered

## Repo_Index
Path | Description
TestCases/LoginModule/ | Login test case Excel files
TestCases/SignupModule/ | Signup test case Excel files
TestCases/CRMContactsModule/ | CRM Contacts test case Excel file
TestCases/SQLTesting/ | SQL testing Excel file
TestCases/APITesting/ | API manual testing Excel file
TestCases/RTM/ | RTM Excel file
TestCases/TestPlan/ | This Test Plan file